## Sheet1
STEPS | WHO |  | WHAT | HOW/NOTES | WHEN
POLLINATOR PLEDGE
|  | FALSE | Sign the Rotary D5060 Pollinator Pledge. Let the District ES Committee know that you and/or club is committed!
|  | FALSE | Review the D5060 Pollinator Highway Project Criteria & Guidelines
|  | FALSE | Use the Pollinator Garden Highway Talking Points & FAQs to give your club leadership a head's up about the project. | Let them know you may need some funding once a design in finalized.
|  | FALSE | Gather a team of Rotarians - Do you have a club Environmental Committee? Perhaps this could be the start? | INTERESTED MEMBERS:
|  | FALSE | Reach out to potential partner organizations, Interact, youth orgs, churches, etc. Keep track of your new contacts! | OUR PARTNER ORGS: (Name/org/email/phone)
|  | FALSE | Read and learn about Pollinator gardens with our Resources
|  | FALSE | Contact local experts; assess the current situation in your area - will your garden be the first? Any other gardens already in your area to use as a model?
|  | FALSE | PREVIEW THE POLLINATOR GARDEN REPORT | Know what info to collect to measure impact
LOCATE
|  | FALSE | Consult with experts for location (i.e Sun, soil, water, human interaction, maintenance, etc.) See our list of possible Community Partners & EXPERTS in your Zone. | OUR EXPERT CONSULTANT: (Name/org/email/phone)
|  | FALSE | Consult with landowners or public stakeholders for possible locations | OUR SITE POSSIBLITIES:
|  | FALSE | Think about visibility: Town entrance; electric vehicle charging stations, Rotary parks | OUR FINAL LOCATION:
|  | FALSE | Take before pics/video | We may make a movie for ESRAG! Make sure to record horizontally!
DESIGN & PREP
|  | FALSE | Consult with experts for design and plant selection. See our links to NATIVE PLANT LISTS.
|  | FALSE | See our list of DESIGN GUIDES & BEST PRACTICES | How big, how many plants? Spring to fall, winter? Continuous blooming, most resilient, etc.
|  | FALSE | See our list of GARDEN CHECKLISTS | Size? Shape? Other hardscape features? Soil prep? Irrigation? Fencing?
|  | FALSE | Cost? Grants? Fundraising? | Budget:
|  | FALSE | Maintenance plan | Be sure to schedule several work dates through out the year. Record your committment in club documents.
|  | FALSE | Consider ordering plants from a local Native Plant Nursery (don't forget to ask business owners to become Rotarians!) | See suppliers in our Resources
PLANT
|  | FALSE | Set a work party date | PLANTING DATE:
|  | FALSE | Gather people - club members, experts, youth groups, RECRUIT new members
|  | FALSE | Work with Partner organizations - offer to volunteer swap and build long-term relationships
|  | FALSE | Gather supplies | Supply List:
|  | FALSE | Get planting! TAKE PICS & VIDEO
REPORT, MAINTAIN & ENJOY
|  | FALSE | Before/After pics/video
|  | FALSE | Complete Report (LINK) (Plant numbers, volunteers, etc.)
|  | FALSE | Get mapped! | ROTARY D5060 POLLINATOR HIGHWAY MAP
|  | FALSE | Receive sign!